## Sheet1
Task | Description | Status
📧 Create root account email | e.g., aws-root@company.com | ☐
📧 Create Log Archive email | e.g., aws-log@company.com | ☐
📧 Create Audit account email | e.g., aws-audit@company.com | ☐
🔐 Enable MFA on root | Use a password manager + MFA device | ☐
💳 Attach valid billing method | Credit card in root account | ☐
📁 Register domain for email routing | Optional but recommended for account emails | ☐
🎛️ Create AWS Organization | Enable all features | ☐
🗺️ Go to Control Tower Console | Link: console.aws.amazon.com/controltower | ☐
🏗️ Launch Landing Zone Setup | Starts wizard | ☐
🏢 Define Organizational Units (OUs) | e.g., Core, Custom, Dev, Prod | ☐
📂 Setup Log Archive & Audit Accounts | Provide unique emails | ☐
🌍 Select home region | e.g., us-east-1, ap-southeast-1 | ☐
🛡️ Enable guardrails (SCPs) | Choose mandatory and strongly recommended | ☐
⏳ Wait for deployment (~1 hr) | Check dashboard for success | ☐
🔐 Setup IAM Identity Center (SSO) | Choose built-in or federate with Azure AD/Okta | ☐
🎫 Create permission sets | Admin, Billing, Developer roles | ☐
👥 Assign users to accounts | Assign SSO users to Dev/Prod accounts | ☐
🧪 Test login | Confirm SSO login works in new accounts | ☐
🧠 Enable Config, GuardDuty, Security Hub | Across accounts | ☐
📦 Deploy AFT framework | Use aws-ia Terraform module | ☐
📁 Setup Git repo for account requests | GitOps model for provisioning | ☐
🧱 Provision new accounts (Dev/UAT/Prod) | Via AFT Terraform modules | ☐
🧬 Customize baselines (VPC, IAM, logging) | Terraform modules in AFT customization pipeline | ☐
🔁 Create automated pipelines | GitHub Actions, CodePipeline | ☐
📌 Define tagging strategy | Tags for cost center, environment, owner | ☐
📈 Enable centralized CloudWatch dashboards | Use log archive or Security Lake | ☐
📜 Enable AWS Config rules | Required for compliance/audit | ☐
🚨 Set up Guardrails alerts | SNS + CloudWatch for SCP violations | ☐
🧾 Define audit log access policy | Centralize to Security/Audit team | ☐
🔄 Setup CloudFormation StackSets | Deploy shared baseline infra | ☐
🔐 Enable Service Catalog | Provide curated infrastructure templates | ☐
🔍 Enable Cost Explorer + Budgets | Set budgets and alerts per account | ☐
🛡️ Add custom SCP policies | Based on business rules | ☐